## Sheet1
TWIPi MB2/PB2 Changes

HW	SW	Discuss	Status	Change description
y		y	done	Move stepper headers for easier access from back panel
y		y	done	Move battery header for easier access from back panel
y			done	Verify USB console data leads - seem to be backwards
		y	TBS	select good locations for mounting hole & clear space
y			done	rework for LED resistors lying down
y			WIP	re-do pinouts document for MB2/PB2, & separate components. Add DRV
y	y		WIP	figure out pullup / pulldown for software readable switch, maybe change Gpio
y		y	WIP	rework to make all grounds bridged, without ground loops
y			done	rework to eliminate DPDT switch, since grounds are all common now
y			done	ground USB Jack shield
y			done	turn around LEDs to simplify ground connections
y	y		WIP	allow s/w control of DRV ENA, disable DRV’s (saving battry) when START = 0
y		y	WIP	design & Layout MOSFET to control battery ADC, and voltage divider
	y		TBS	read ADC, calculate & display battery voltage
	y		WIP	make wheel speed changes immediately
	y		TBS	use conditional definitions for MB2 Gpio definitions and features
y			done	Fix LCD header to allow straight through cable to LCD I2C interface
y		y	WIP	figure out correct LED resistor values and test
		y	TBS	Decide on trace widths for MB2 and PB2
	y		WIP	Extend IMU warmup, minimizing boot time
y		y	TBS	avoid physical conflict between ESP32, console cable, and headers
y		y	WIP	optimize MB2 location by shifting 25 pin connector on PB2
		y	TBS	add an externally accessible jack to allow direct measurement of battery level

Testing needed
				verify angle is accurate with restored IMU warmup
				console works if power coming from battery
				software readable switch can be read
				reworked LEDs and resistors work, and have reasonable brightness
				battery measurement is accurate
				verify Wheels freewheel when START = 0
				verify LCD works with straight through cable
				verify selected trace width can be manufactured
				confirm MB2 and PB2 physically mate without component collisions